- Summary

Title: 	Consultancy for Assessment on potential of community based tourism in the area of Nga Nam Town, Soc Trang province

- Assessment on potential of community based tourism (CBT) development in Nga Nam Town

- recommendations for the spots suitable for CBT placement

Position: 	1 consultant (National)

Duration & timing: 	maximum 9 working days from March 16 to April 15, 2020

Duty station: 	Home, Hanoi, project communes (Vinh Quoi, Tan Long, My Binh) in Nga Nam Town, Soc Trang Province

Reporting:	The Consultative Institute for Socio-Economic Development of Rural and Mountainous Areas – CISDOMA

- Background

Soc Trang is located in the Mekong Delta region. The province is the poorest provinces in Mekong Delta with 57,814 people living below poverty line. Nga Nam is the lowest-lying areas of Soc Trang, which has the population around 80,168 inhabitants (in 2010), and an area of 242,24 km, equating to a density of 331 people per km2. Predominate local ethnic group is Kinh (92.3%), with a Khmer ethnic minority (6.6%).  A lack of adequate local infrastructure, including roads, drainage, irrigation systems, schools, clinics, and social service facilities, serves as a barrier to upward social mobility. Virtually the entire population depends on the agriculture sector for their livelihood.

CISDOMA has bên working in Nga Nam since 2017 with interventions to support livelihood for poor communities in Nga Nam. From the experiences and lessons-learnt in the last two years, this project is designed to further enhance the results that have achieved in the previous period. Major interventions will be focussed on:

Capacity building on following major subjects:

- Self-help group (SGH) operation;

- Market oriented production planning;

- Village saving and lending associations (VSLA) operation;

- Adaptive measuremengt for livelihood improvement.

Support farmers toimplement livelohoods with adaptive measurments:

- Individual household: Continue to support selected adaptive livelihood activities that initiated in the first phase (table bellow) with focus on further expansion, improved quality, production planing/organisation and market connection

- Collective: Enhance the coordination, planning, cooperative groups, improved quality, production, initial proccessing, packaging, branding, and market connection.

- VSLA: Provide technical support and innitial operational cost

- Non-farm livelihoods (embrodery, community tourism...)

- Purpose

CISDOMA is seeking for a consultant (National) to (i) Assessment on potential of community based tourism (CBT) development in Nga Nam Town (ii) recommendations for the spots suitable for CBT placement and a development plan for building a CBT model in Nga Nam

- Scope and the methodology

The consultant is expected to use a panel of methods and tools including (i) secondary data review, (ii) interviews of key informants (PMU, functional agencies in Nga Nam, tourist companies, CISDOMA project team), (iii) field and households visits, and (iv) group discussions with households, self-help-groups, and appropriate tools for analysis of community based tourism

- Deliverables:

- A detailed plan which include set of tools and methodology, and schedule for the evaluation

- Report outline prior to going for field trip

- Records/minutes of all meetings/consultations conducted;

- Final report (in Vietnamese).

- Outputs/ deliverables

| No | Term of actions | Timelines | Responsibility | Note |
| --- | --- | --- | --- | --- |
| 1 | Consultant selection | Feb 25 to Mar 9, 2020 | CISDOMA/Project |  |
| 2 | Review of project documents & reports, secondary data... and consultant contract signed | Mar 10 to Mar 15, 2020 | Consultant(s) |  |
| 3 | Field data collection in Nga Nam, Soc Trang Province | 3 days in the 3rd or 4th week of Mar 2020 | Consultant(s) | CISDOMA support logistic arrangement |
| 4 | Analysis, report writing and first draft Submission | Before 10th April 2020 | Consultant(s) |  |
| 6 | Finalized reports | By April 20, 2020 | Consultant(s) |  |

Role of the Partners

In support of the consultancy CISDOMA will make their staff available for discussing the strategic approach of the assignment as well as to discuss content and review the draft versions of the reports. CISDOMA will ensure the logistic and human resource support for the organization of meetings, the field level study.

- Consultant profile

The consultant/consultancy team shall have the following skills and experience.

- At least 5 years of theoretical and practical work on tourism, livelihood including all crosscutting issues (gender)

- Previous experience working in community based tourism is an advantage

- Excellent communication and documentation skills in English and Vietnamese

- Results focused and accountable

The consultants are expected to provide samples of previous assignments with a similar content.

- Consultancy Management

The consultant will officially report to CISDOMA. CISDOMA will be responsible for the coordination with  other relevant stakeholders in the field.

- Date and timeframe

Maximum 9 working days over the period from March 15 to April 15, 2020

- Consultant Fee

Consultancy rate per day basis, including PIT, will be negotiated based on quality and experience of the consultant. Expenses in the field (transport, accommodation, stationaries….) will be covered by the project at CISDOMA’s cost norm. CISDOMA will not pay any health/ accident insurance. The consultant /consultancy team will have to ensure its own health and accidental insurance.

- Application Procedure

Interested candidates are invited to contact Mrs. Nguyen Thi Thanh Nha (nha.ntt@cisdoma.org.vn) for additional details about the assignment and then to send their applications by email in English consisting of a CV, a letter of motivation and a financial and technical offer to: nha.ntt@cisdoma.org.vn Please indicate clearly your application subject: “BfW CISDOMA - Mid-term Evaluation consultant”.

Deadline for application:   9th March, 2020 at 17:00, Hanoi time. Please note that only applications which are submitted in English and contain all above mentioned documents shall be considered. While

CISDOMA appreciates all responses, only candidate under consideration shall be contacted for an interview.

# Comments

Bác cân nhắc xem mình nên yêu cầu b/c tiếng Việt hay tiếng Anh nhé.

# Text boxes

TERMS OF REFERENCE

Strengthen the resilience of poor population through climate change adaptive livelihoods

Consultancy for Assessment on potential of community based tourism in the area

of Nga Nam Town, Soc Trang province